## Sheet1
Red Posts: AJAX to avoid sending bigass datasets	???
Red Posts: Filter gameplay/balance
Navbar: Button instead of <a>	15			because class
Articles: Check when title is void	50
Champions Additional Fields	101	0.5		State, Articles, SWOT etc
Listes : AJAX	999
Smartass comments	1000	0.5		'Riot Rework Riven', 'N Days Since Irelia was Released', etc.	With User Friendly URLs !
Server: Interface EVE	999999	1		Not in LoD v1.0 !
Items Design	999999			Not in LoD v1.0 !
Champion Patches	999999			Not in LoD v1.0 !
Champions: Manage Double Forms	999999			Jayce, Elise have trouble with icons
Champions: Special	999999			Kalista for instance, Viktor, Rengar
Champions: Sort by Resource	999999
Champions: Hard Coded fixes (Multi spells, etc.)	999999
Functionality	Priority	Time (days)	Completed	Comment		*Alpha is a rough, functional draft.
Articles: Type, Dates, on read page
Champions Grid: Focus on search
Articles: Exception on Champion_Data
Articles: Main page (news)
Server Logic: Errors on the Article page
Articles: Interface Auto-gen URL
Script : Automate				Python Script : #!/usr/bin/env python ==> special virtual env !
Articles: Postimport after edit
Interface: Security
Base de données: Check UP/DOWN
Champions: Articles Map/Reduce				DATE ! + Check url_id 'cuz It can break
Red Posts : Page Principale (with search)
Red Posts : Hide the bigger ones
General Terms & Condition				must be somewhere !
Champions: Resource not ok
Interface: Search (alpha)
Interface: Modify Article
Interface: Modify Champion (alpha)				State
Django: Base LoD Application				views, urls, etc.
Interface: Champion (alpha)
Interface: Homepage (alpha)
Django: Query Consumer				He might be our integrated Python Eve so some work for us
Champions: Special names				Twisted Fate (tf), etc.	Done for the Grid view
Images: Traitement et Rename
Environnement de développement			08/06/15
Architecture serveur			08/06/15
Définition du cahier des charges			09/06/15
Récupération des champions			09/06/15
Récupération des Red Posts			09/06/15
Map/Reduce Champions			09/06/15
Map/Reduce Red Posts			10/06/15
Association Red Posts/Champions			10/06/15
Algorithme RPC v1.0			10/06/15